## Sheet1
Category | Date | Completed_Forecast Date | KPI | KPI Description
Business Case development commenced | 2021-09-20 | 2021-09-25 | Black | Completed
First Design Phase funding approved | 2021-11-28 | 2021-11-28 | Black | Completed
Business Case endorsed and approved by Executive Committee | 2022-03-31 | 2022-04-30 | Black | Completed
Procurement recommendation approved | 2022-04-10 | 2022-04-10 | Black | Completed
Software and licensing procured | 2022-05-19 | 2022-05-19 | Black | Completed
Detailed schedule finalised and Chief Architect approved | 2022-06-06 | 2022-06-06 | Black | Completed
Change Management Strategy Approved | 2022-10-14 |  | Red | Overdue > 10 days
Integration checkpoint | 2022-11-03 | 2022-11-15 | Black | Completed
Compliance and first run achieved | 2023-04-20 | 2023-04-30 | Black | Completed
Integration testing completed and signed off | 2023-08-30 | 2023-09-10 | Yellow | At Risk
Final Design Phase funding approved | 2023-08-10 | 2023-08-10 | Yellow | At Risk
Final Design Phase completed and approved | 2023-09-30 | 2023-09-30 | Green | On-track
End user training completed | 2023-10-31 | 2023-10-31 | Green | On-track
End to End UAT completed and signed off | 2023-11-07 | 2023-11-07 | Green | On-track
Decision on deplopyment to Production | 2023-11-04 | 2023-11-04 | Green | On-track
Reporting delivered and approved by Executive Committee | 2023-12-18 | 2023-12-18 | Green | On-track
Hypercare completed | 2024-01-30 | 2024-01-30 | Green | On-track
Benefits enabled | 2024-01-30 | 2024-01-30 | Green | On-track
Project Closure Signed-Off | 2024-02-11 | 2024-02-11 | Green | On-track